## PMP
Review No. | Raised By | Issue Date | Issue | Status | Approved By | Closed date
PMP_1_Quality_Managment_Plan | Fatma | 15/4/2022 | Pages Number need to be modified | Close
PMP_2_Quality_Managment_Plan | Fatma | 15/4/2022 | In 1.1 section, following a good process need to be mentioned | Open
PMP_3_Quality_Managment_Plan | Fatma | 15/4/2022 | In section 2.2 Environment and tools in impelementation needs to be added | Close
PMP_4_Schedule/TIme_Management | Fatma | 15/4/2022 | In section 2.2 figures 2.1 and 2.2 are reversed | Open
PMP_5_Schedule/TIme_Management | Fatma | 15/4/2022 | In section 2.2 the functionality of record void, rename it to uploadRec ordVoice | Open
PMP_6_ConfigurationManagment | Fatma | 15/4/2022 | In section 4.1 Tailoring need to be more specific by clarfying its meaning to the customer in the glossary | Open
PMP_7_ConfigurationManagment | Fatma | 15/4/2022 | In section 4.2 basline need to be more specific by clarfying its meaning to the customer in the glossary | Open
PMP_8_Appendix A | Fatma | 15/4/2022 | missing this section in PMP document | Open
PMP_9_Appendix A | Fatma | 15/4/2022 | Missing WBS Dicetionary location | Open
PMP_10_Appendix A | Fatma | 15/4/2022 | Cannot open any of the links provided in location section | Open
PMP_11_Risk_Management_plan | Radwa | 15/4/2022 | The Pages Number in the table of conent don't match the actual data the page numbers need to be updated | Open | Delete ya radwa
PMP_12_Risk_Management_plan | Radwa | 15/4/2022 | In 1.1 : Risk Management definition sentence need to be restructured | Close
PMP_13_Risk_Management_plan | Radwa | 15/4/2022 | in 2.3.1 Probability : The Definitions of each probability need to be rephrase | Open
PMP_14_Risk_Management_plan | Radwa | 15/4/2022 | in 2.4 in Mitigate : their is a spelling mistake "like adding more tests around the hi-risk areas" | Close
PMP_15_Risk_Management_plan | Radwa | 15/4/2022 | in Appendix A : The Default message need to be changed | Open
PMP_16_Risk_Management_log | Radwa | 15/4/2022 | Identify the Risk Areas Categories in the instructions | Open
PMP_17_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log : Risk Management Log is duplicated | Open
PMP_18_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log in RI_0 in Project Impact: The sentence need to be rephrase | Open
PMP_19_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log in RI_3 in Risk Area : Budget need to be added | Open
PMP_20_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log in RI_3 in Contingency Plan : non practical solution | Open
PMP_21_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log the ID number 4 is missing and the the IDs starts with number 0 | Open
PMP_22_Risk_Management_log | Radwa | 15/4/2022 | Grammer : In Risk_Tracking_Log in RI_5 in Project Impact : "some teams can't continue their job" | Open
PMP_23_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log in RI_5 in Risk Area : Resources need to be added | Open
PMP_24_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log in RI_6 swap Response Strategy with Contigency plan | Open
PMP_25_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log Add a name column | Open
PMP_26_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log Change the ID naming convension | Open
PMP_27_Issue_Management_Esclation Plan | Yara | 15/4/2022 | Project manager role should also be responsilbe for effectively manage and monitor issues on a regular basis, follow up with issue owners to ensure progress is being made towards resolution, and to report on the status of issues. | Open
PMP_28_Issue_Management_Esclation Plan | Yara | 15/4/2022 | step 4 2.2 "jeopardize" i think choose another simple word | Open
PMP_29_Project_Charter | Yara | 15/4/2022 | Project Name : Encyclopedia learning Hub | Open
PMP_30_Project_Charter | Yara | 15/4/2022 | 1. project Goals 1.1 Organ Objectives 1.1.7 schedule 5 weeks - 160 Hours (4 Hours every day) | Open
PMP_31_Project_Charter | Yara | 15/4/2022 | 1.project Goals 1.3 project specific objectives 1.3.1 web application not website | Open
PMP_32_Project_Charter | Yara | 15/4/2022 | 2.Deliverable . add PMP aslo | Open
PMP_33_Scope_Statement | Yara | 15/4/2022 | Scope Description In Scope Design --Web application not Website | Open
PMP_34_Scope_Statement | Yara | 15/4/2022 | Constraints Scope --Web application not Website | Open
PMP_35_WBS | Yara | 15/4/2022 | 3.1.6 Choose Categories not Seacrh for Categories | Open
PMP_36_WBS | Yara | 15/4/2022 | 3.2.5 Choose Categories not Seacrh for Categories | Open
PMP_37_WBS | Yara | 15/4/2022 | Missing "e" in word Encyclopedia web application | Open
PMP_38_WBS_Dictionary | Yara | 15/4/2022 | 1.2 Task Owner "yara&fatma" | Open
PMP_39_Introduction | Yara | 15/4/2022 | 1.2.1 web application not website | Open
PMP_40_Introduction | Yara | 15/4/2022 | 1.2.2 web application not website categories not fields | Open
PMP_41_Introduction | Yara | 15/4/2022 | 1.2.3 schedule 5 weeks - 160 Hours (4 Hours every day) | Open
PMP_42_Introduction | Yara | 15/4/2022 | 1.2.4 Maha: Designer | Open
PMP_43_Introduction | Yara | 15/4/2022 | 1.3.2 NO.4 only 3 admin features not 4 | Open

## SRS
Review No. | Raised By | Issue Date | Issue | Status | Approved By | Closed date
SRS_Version 1.0 | Mai | 15/4/2022 | Is each requirement atomic? | Close | Mai | 15/4/2022
| Mai | 15/4/2022 | Is each requirement Feasible? | Close | Mai | 15/4/2022
| Maha | 15/4/2022 | Is each requirement Understandable? | Close | Maha | 15/4/2022
| Rana | 14/04/2022 | Is each requirement has assigned priority? | Close | Rana | 15/04/2022
| Mai | 15/4/2022 | Is each requirement has a version? | Close | Mai | 15/4/2022
| Rana | 15/04/2022 | Are some software requirement traceable to its verification criteria? | Close | Rana | 15/04/2022
| Maha | 15/4/2022 | Is each software requirement traceable to a system requirement? | Close | Maha | 15/4/2022
| Rana | 15/04/2022 | Is each software requirement traceable to the system architecture? | Close | Rana | 15/04/2022

## Options (hidden)
Open
Close

## Progress_Chart
PMP | Open | 39 | SRS | Open | 0
| Closed | 0 |  | Closed | 0
| Total | 39 |  | Total | 0