## WBS Dictionary
WORK BREAKDOWN STRUCTURE DICTIONARY
| PROJECT TITLE | PROJECT ID | COMPANY |  |  | VERSION
| Web application Encyclopedia | Team C | ITI |  |  | 1.0.0
TASK ID | TASK DESCRIPTION | DEPENDENT UPON | TASK OWNER | TASK STATUS | BEGIN DATE | DATE OF COMPLETION | ADDITIONAL INFO
1 | Planning |  |  | 100%
1.1 | Project Management Plan | (2.1.1 - 2.1.8) | Mai, Maha, Rana | 100% | 2022-10-04 | 15/4/2022
1.1.1 | Scope Management Plan | 1.1.1 | Mai | 100% | 2022-11-04 | 15/4/2022
| Project Charter | N/A | Maha , Mai | 100% | 2022-10-04 | 15/4/2022
1.1.2 | Change Management Plan | N/A | N/A | 0% | N/A | N/A | This plan will not be included in this phase.
1.1.3 | Schedule Time Management | 1.1.1 | Mai | 100% | 2022-12-04 | 22/4/2022
1.1.3.1 | MileStones | 1.1.1 | Radwa | 100% | 2022-11-04 | 15/4/2022
1.1.3.2 | Project Schedule | 1.1.1 | Radwa | 100% | 2022-11-04 | 15/4/2022
1.1.3.2 | Dependencies | 1.1.1 | Radwa | 100% | 2022-11-04 | 15/4/2022
1.1.4 | Quality Managemnt Plan | 3 | Rana | 100% | 2022-11-04 | 15/4/2022
1.1.5 | Configuration Management Plan | 4 | Rana | 100% | 2022-11-04 | 15/4/2022
1.1.6 | Commuincation Management Plan | 2.1.6.1 | Mai | 100% | 2022-10-04 | 15/4/2022
1.1.6.1 | Commuincation Matrix | 2.1.6 | Mai | 100% | 2022-10-04 | 15/4/2022
1.1.7 | Risk Management Plan | 7 | Maha | 100% | 2022-11-04 | 15/4/2022
1.1.7.1 | Risk Log | 2.1 | Mai | 100% | 2022-11-04 | 15/4/2022
1.2 | SRS | N/A | Yara, Fatma, Radwa | 100% | 2022-10-04 | 22/4/2022
1.2.1 | SIQ | 1.2 | All Team | 100% | 2022-09-04 | 2022-12-04
1.3 | Frameworks & Tools | 1.3.3 | Mai | 100% | 2022-12-04 | 15/4/2022
2 | Implementation and Execurion |  |  | 0%
2.1 | Solution Design | 2.1.1 | N/A | 0%
2.1.1 | Prototype | 2.1.1 | N/A | 0%
2.1.2 | Layout Design | 2.1.1 | N/A | 0%
2.2 | Design | 3.1 | N/A | 0%
2.2.1 | Front-End Design | N/A | N/A | 0%
2.2.2 | Back-End Design | N/A | N/A | 0%
2.3 | Development |  | N/A | 0%
2.3.1 | Front-End Development | 3.2.1 | N/A | 0%
2.3.2 | Back-End Development | 3.2.2 | N/A | 0%
2.4 | Content & SEO | 3.3 | N/A | 0%
2.5 | Testing | (3.1- 3.4) | N/A | 0%
2.5.1 | Experience-Based Testing | (3.3.1- 3.3.2) | N/A | 0%
3 | Mointoring and Control |  |  | 0%
3.1 | Traceability Matrix | 2.1 | N/A | 0%
3.2 | Version Control | 2.1.5 | N/A | 0%
4 | Closing |  |  | 0%
4.1 | Deployment Phase | 3.5 | N/A | 0%