## PMP
ID | Raised By | Issue Date | Issue | Status | Approved By | Closed date
PMP_1_Quality_Managment_Plan | Fatma | 15/4/2022 | Pages Number need to be modified | Close | Fatma | 15/04/2022
PMP_2_Quality_Managment_Plan | Fatma | 15/4/2022 | In 1.1 section, following a good process need to be mentioned | Close | Fatma | 15/04/2022
PMP_3_Quality_Managment_Plan | Fatma | 15/4/2022 | In section 2.2 Environment and tools in impelementation needs to be added | Close | Fatma | 15/04/2022
PMP_4_Schedule/Time_Management | Fatma | 15/4/2022 | In section 2.2 figures 2.1 and 2.2 are reversed | Close | Fatma | 15/4/2022
PMP_5_Schedule/Time_Management | Fatma | 15/4/2022 | In section 2.2 the functionality of record void, rename it to uploadRec ordVoice | Close | Fatma | 15/4/2022
PMP_6_ConfigurationManagment | Fatma | 15/4/2022 | In section 4.1 Tailoring need to be more specific by clarfying its meaning to the customer in the glossary | Close | Fatma | 15/4/2022
PMP_7_ConfigurationManagment | Fatma | 15/4/2022 | In section 4.2 basline need to be more specific by clarfying its meaning to the customer in the glossary | Close | Fatma | 15/4/2022
PMP_8_Appendix A | Fatma | 15/4/2022 | missing this section in PMP document | Close | Fatma | 15/4/2022
PMP_9_Appendix A | Fatma | 15/4/2022 | Missing WBS Dicetionary location | Close | Fatma | 15/4/2022
PMP_10_Appendix A | Fatma | 15/4/2022 | Cannot open any of the links provided in location section | Close | Fatma | 15/4/2022
PMP_11_Risk_Management_plan | Radwa | 15/4/2022 | The Pages Number in the table of conent don't match the actual data the page numbers need to be updated | Close | Radwa | 15/4/2022
PMP_12_Risk_Management_plan | Radwa | 15/4/2022 | In 1.1 : Risk Management definition sentence need to be restructured | Close | Radwa | 15/4/2022
PMP_13_Risk_Management_plan | Radwa | 15/4/2022 | in 2.3.1 Probability : The Definitions of each probability need to be rephrase | Close | Radwa | 15/4/2022
PMP_14_Risk_Management_plan | Radwa | 15/4/2022 | in 2.4 in Mitigate : their is a spelling mistake "like adding more tests around the hi-risk areas" | Close | Radwa | 15/4/2022
PMP_15_Risk_Management_plan | Radwa | 15/4/2022 | in Appendix A : The Default message need to be changed | Close | Radwa | 15/4/2022
PMP_16_Risk_Management_log | Radwa | 15/4/2022 | Identify the Risk Areas Categories in the instructions | Close | Radwa | 15/4/2022
PMP_17_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log : Risk Management Log is duplicated | Close | Radwa | 15/4/2022
PMP_18_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log in RI_0 in Project Impact: The sentence need to be rephrase | Close | Radwa | 15/4/2022
PMP_19_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log in RI_3 in Risk Area : Budget need to be added | Close | Radwa | 15/4/2022
PMP_20_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log in RI_3 in Contingency Plan : non practical solution | Close | Radwa | 15/4/2022
PMP_21_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log the ID number 4 is missing and the the IDs starts with number 0 | Close | Radwa | 15/4/2022
PMP_22_Risk_Management_log | Radwa | 15/4/2022 | Grammer : In Risk_Tracking_Log in RI_5 in Project Impact : "some teams can't continue their job" | Close | Radwa | 15/4/2022
PMP_23_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log in RI_5 in Risk Area : Resources need to be added | Close | Radwa | 15/4/2022
PMP_24_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log in RI_6 swap Response Strategy with Contigency plan | Close | Radwa | 15/4/2022
PMP_25_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log Add a name column | Close | Radwa | 15/4/2022
PMP_26_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log Change the ID naming convension | Close | Radwa | 15/4/2022
PMP_27_Issue_Management_Esclation Plan | Yara | 15/4/2022 | Project manager role should also be responsilbe for effectively manage and monitor issues on a regular basis, follow up with issue owners to ensure progress is being made towards resolution, and to report on the status of issues. | Close | Yara | 15/4/2022
PMP_28_Issue_Management_Esclation Plan | Yara | 15/4/2022 | step 4 2.2 "jeopardize" i think choose another simple word | Close | Yara | 15/4/2022
PMP_29_Project_Charter | Yara | 15/4/2022 | Project Name : Encyclopedia learning Hub | Close | Yara | 15/4/2022
PMP_30_Project_Charter | Yara | 15/4/2022 | 1. project Goals 1.1 Organ Objectives 1.1.7 schedule 5 weeks - 160 Hours (4 Hours every day) | Close | Yara | 15/4/2022
PMP_31_Project_Charter | Yara | 15/4/2022 | 1.project Goals 1.3 project specific objectives 1.3.1 web application not website | Close | Yara | 15/4/2022
PMP_32_Project_Charter | Yara | 15/4/2022 | 2.Deliverable . add PMP aslo | Close | Yara | 15/4/2022
PMP_33_Scope_Statement | Yara | 15/4/2022 | Scope Description In Scope Design --Web application not Website | Close | Yara | 15/4/2022
PMP_34_Scope_Statement | Yara | 15/4/2022 | Constraints Scope --Web application not Website | Close | Yara | 15/4/2022
PMP_35_WBS | Yara | 15/4/2022 | 3.1.6 Choose Categories not Seacrh for Categories | Close | Yara | 15/04/2022
PMP_36_WBS | Yara | 15/4/2022 | 3.2.5 Choose Categories not Seacrh for Categories | Close | Yara | 15/04/2022
PMP_37_WBS | Yara | 15/4/2022 | Missing "e" in word Encyclopedia web application | Close | Yara | 15/04/2022
PMP_38_WBS_Dictionary | Yara | 15/4/2022 | 1.2 Task Owner "yara&fatma" | Close | Yara | 15/4/2022
PMP_39_Introduction | Yara | 15/4/2022 | 1.2.1 web application not website | Close | Yara | 15/4/2022
PMP_40_Introduction | Yara | 15/4/2022 | 1.2.2 web application not website categories not fields | Close | Yara | 15/4/2022
PMP_41_Introduction | Yara | 15/4/2022 | 1.2.3 schedule 5 weeks - 160 Hours (4 Hours every day) | Close | Yara | 15/4/2022
PMP_42_Introduction | Yara | 15/4/2022 | 1.2.4 Maha: Designer | Close | Yara | 15/4/2022
PMP_43_Introduction | Yara | 15/4/2022 | 1.3.2 NO.4 only 3 admin features not 4 | Close | Yara | 15/4/2022
WBS_44_Project_Managment_Plan | Fatma | 30/4/2022 | Depends on 2.1.1(wrong dependency) and 2.1.8 (doesn't exist) | Close | Fatma | 2022-06-05
WBS_45_Quality_Managment_Plan | Fatma | 30/4/2022 | how it depends on number 3 | Close | Fatma | 2022-06-05
WBS_46_Configuration_Managment_Plan | Fatma | 30/4/2022 | how it depends on number 4 | Close | Fatma | 2022-06-05
WBS_47_Communication_Managment_Plan | Fatma | 30/4/2022 | 2.1.6 dependeoncy does not exist | Close | Fatma | 2022-06-05
WBS_48_Communication_Matrix | Fatma | 30/4/2022 | 2.1.6 dependency does not exist | Close | Fatma | 2022-06-05
WBS_49_Risk_Managment_Plan | Fatma | 30/4/2022 | 7 dependency doesnot exist | Close | Fatma | 2022-06-05
WBS_50_Risk_Log | Fatma | 30/4/2022 | risk log depends on wireframe design? | Close | Fatma | 2022-06-05
WBS_51_Frameworks&Tools | Fatma | 30/4/2022 | Dependency 1.3.3 doesnot exist | Close | Fatma | 2022-06-05
PMP_52_Revision_Date | Fatma | 30/4/2022 | missing revision date in version 1.2 | Close | Fatma | 2022-06-05
PMP_53_Folder_Structure_Concept | Fatma | 30/4/2022 | WBS is not in the concept folder | Close | Fatma | 2022-06-05
PMP_54_Folder_Structure_Definition_Design_HL | Fatma | 30/4/2022 | missing sequence diagram,erd,usecase and wireframes | Close | Fatma | 2022-06-05
PMP_55_Folder_Structure_Definition_Design_LL | Fatma | 30/4/2022 | missing sequence diagram | Close | Fatma | 2022-06-05
PMP_56_Folder_Structure_Definition_Requirements | Fatma | 30/4/2022 | missing validation specification | Close | Fatma | 2022-06-05
PMP_57_Folder_Structure_onitor&Control_Quality_Managment_Plan | Fatma | 30/4/2022 | missing audits and teceability matrix | Close | Fatma | 2022-06-05

## Design
ID | Raised By | Issue Date | Issue | Status | Approved By | Closed date
HLSD_01_Admin | Radwa | 30/4/2022 | File Name doesn't follow tha naming convension | Close | Radwa | 30/4/2022
HLSD_02_Admin | Radwa | 30/4/2022 | In SRS there is a condition if there is a poor connection in both the Functionalities | Close | Radwa | 30/4/2022
HLSD_03_RegisteredUser | Radwa | 30/4/2022 | There is no functionality called "clickOnSpecificCategory" | Close | Radwa | 30/4/2022
HLSD_04_RegisteredUser | Radwa | 30/4/2022 | Missing Functionality (Follow specific categories) | Close | Radwa | 30/4/2022
ERD_05 | Radwa | 30/4/2022 | The ID of each Entities aren't Unique | Close | Radwa | 30/4/2022
LLSD_06 | Mai | 30/4/2022 | The IDs of all diagrams don't match the SRS Features IDs | Close | Mai | 2022-04-05
LLSD_07_02AU | Mai | 30/4/2022 | in SRS, there is no mention that after logged in, the admin/user will be redirected to Home Page | Close | Mai | 2022-04-05
LLSD_08_03AU | Mai | 30/4/2022 | in SRS, there is no mention that after logged out, the admin/user will be redirected to Home Page | Close | Mai | 2022-04-05
LLSD_09_04AU | Mai | 30/4/2022 | Feature ID in SRS doesn't match ID in Diagram itself and Diagram's Name | Close | Mai | 2022-04-05
LLSD_10_04AU | Mai | 30/4/2022 | rectangle of Actor is missing "Admin" as an actor with User | Close | Mai | 2022-04-05
LLSD_11_04AU | Mai | 30/4/2022 | the button go in SRS but it doesn't found in the diagram | Close | Mai | 2022-04-05
LLSD_12_05U | Mai | 30/4/2022 | in SRS, there is no mention that after choosing category, the admin/user will be redirected to Category Page | Close | Mai | 2022-04-05
LLSD_13_05U | Mai | 30/4/2022 | in SRS, there is no mention that after publishing article, the admin/user will be redirected to be Redirected To Publish Article Page | Close | Mai | 2022-04-05
LLSD_14_06U | Mai | 30/4/2022 | in SRS, there is no mention that after choosing category, the admin/user will be redirected to Category Page | Close | Mai | 2022-04-05
LLSD_15_06U | Mai | 30/4/2022 | in SRS, there is no mention that after uploading video, the admin/userwill be redirected to be Redirected To Upload Video Page | Close | Mai | 2022-04-05
LLSD_16_08U | Mai | 30/4/2022 | In FR8_U the function name is different "upload Recorded Voice" | Close | Mai | 2022-04-05
Validation_17_UC_01 | Maha | 30/4/2022 | Web site not web application | Close | Maha | 2022-04-05
Validation_18_UC_01 | Maha | 30/4/2022 | Postconditions: created succssfully not "in" | Close | Maha | 2022-04-05
Validation_19_UC_02 | Maha | 30/4/2022 | "Login button will not be activated until the user fill all required fields" activated is not clear | Close | Maha | 2022-04-05
Validation_20_UC_03 | Maha | 30/4/2022 | postconditions: "The system shall display home page wit register & login button"mistake in "with" | Close | Maha | 2022-04-05
Validation_21_UC_04 | Maha | 30/4/2022 | "Main success scenario: Click on go button" there's no go button | Close | Maha | 2022-04-05
Validation_22_UC_04 | Maha | 30/4/2022 | Extentions: step 3 "User forget to choose " why the system gives alert if the user didn't choose? | Close | Maha | 2022-04-05
Validation_23_UC_09 | Maha | 2022-01-05 | Extentions: c- "either cutting the record in to several records or canceling the uploading process" | Close | Maha | 2022-06-05
Validation_24_UC_10 | Maha | 2022-01-05 | Choose language feature for admin and user | Close | Maha | 2022-04-05
Validation_25_UC_10 | Maha | 2022-01-05 | "User navigates through the website to show the Language section" in the navigation bar | Close | Maha | 2022-04-05
Validation_26_UC_10 | Maha | 2022-01-05 | Extentions: "alert" why alert if he didn't choose? it should be "if the desired language didn't appear" | Close | Maha | 2022-04-05
Validation_27_UC_12 | Maha | 2022-01-05 | "admin shall be able to delete any content" specifiy content | Close | Maha | 2022-04-05
Usecase_28 | Rana | 2022-01-05 | Missing user without register actor | Close | Rana | 2022-04-05
Usecase_29 | Rana | 2022-01-05 | Link new actor with "choose category & choose language & Register" use cases | Close | Rana | 2022-04-05
Usecase_30 | Rana | 2022-01-05 | Admin actor missing linking with "choose language" use case | Close | Rana | 2022-04-05
Wireframe_31_Admin | Rana | 2022-01-05 | Missing language button | Close | Rana | 2022-04-05
Wireframe_32_Registered user | Rana | 2022-01-05 | Missing language button | Close | Rana | 2022-04-05
Wireframe_33_Registered user | Rana | 2022-01-05 | In SRS in "Publish article,Upload video,Upload record" it doesn't mention that there Post dropdown list to choose from it it says button | Close | Rana | 2022-04-05
Wireframe_34_Registered user | Rana | 2022-01-05 | In SRS "Publish article" it is mention that the article will be uploaded not typed | Close | Rana | 2022-04-05
Wireframe_35_Registered user | Rana | 2022-01-05 | In SRS in "Publish article,Upload video,Upload record" it specify button name "Submit" and in wireframe it specify button name "Post" | Close | Rana | 2022-04-05
Wireframe_36_Registered user | Rana | 2022-01-05 | In wireframe "Upload video & Upload record" missinng buttons "browse","Upload", "Submit" | Close | Rana | 2022-04-05
Wireframe_37_Registered user | Rana | 2022-01-05 | In wireframe missing followed category page for notificatons | Close | Rana | 2022-04-05
Wireframe_38_Registered user | Rana | 2022-01-05 | In wireframe missing notification itself how it will be showed to user | Close | Rana | 2022-04-05
Wireframe_39_Registered user | Rana | 2022-01-05 | Is the bill icone for accessing nitification and followed category page or for following a specific category ?? if it is nfor following a specific category it only need to be showed in catego page but if it is for accessing followed categories then where is the following button in the category page | Close | Rana | 2022-04-05
Wireframe_40_Unregistered user | Rana | 2022-01-05 | missing choose language button | Close | Rana | 2022-04-05
FR11_AU_41_missed sequence Diagram | yara | 2022-03-05 | In the low level design there is sequence diagram missed for the system feature number 11 FR11_AU | Close | yara | 2022-04-05
FR1_UWR_42_missed sequence Diagram | yara | 2022-03-05 | In the low level design there is sequence diagram missed for the system feature number 1 | Close | yara | 2022-04-05

## SRS
Review No. | Raised By | Issue Date | Issue | Status | Approved By | Closed date
SRS_Version 1.0 | Mai | 15/4/2022 | Is each requirement atomic? | Close | Mai | 15/4/2022
| Mai | 15/4/2022 | Is each requirement Feasible? | Close | Mai | 15/4/2022
| Maha | 15/4/2022 | Is each requirement Understandable? | Close | Maha | 15/4/2022
| Rana | 14/04/2022 | Is each requirement has assigned priority? | Close | Rana | 15/04/2022
| Mai | 15/4/2022 | Is each requirement has a version? | Close | Mai | 15/4/2022
| Rana | 15/04/2022 | Are some software requirement traceable to its verification criteria? | Close | Rana | 15/04/2022
| Maha | 15/4/2022 | Is each software requirement traceable to a system requirement? | Close | Maha | 15/4/2022
| Rana | 15/04/2022 | Is each software requirement traceable to the system architecture? | Close | Rana | 15/04/2022

## Options
Open
Close

## Progress_Chart
PMP | Open | 0 | SRS | Open | 0
| Closed | 57 |  | Closed | 8
| Total | 57 |  | Total | 8
Design | Open | 0
| Close | 42
| Total | 42