## Review Process
Review Process
Review No. | Review ID for every single new review comment
Raised By | Write the reviewer's name, the reviewers shouldn’t be the authors of files
Issue Date | Date of issue when found
Issue | detailed description of issue found by the reviewer in the document
Status | set the status (Open/Closed)
Approved By | Write the reviewer's name, this shouldn’t beapproved by the authors of files
Closed date | Date of issue when closed and approved
1. The reviewer must document every finding or issue in the review sheet
2. All issues must be closed before delivering the milestone
3. Reviewers of document can't be the authors of files
4. Any new document will be reviewed added in new sheet with the name of document
5. If issue description was unclear, the author should ask the reviewer and discuss the comment together
6. The reviewer must approve the finding solved in the document to be considered close issue
7. Sheet of review is an online sheet "google excel sheet", the sheet is shared between the whole team.
8. when review is done, the sheet must be downloaded as an excel sheet and then pushed to the repo.

## SDD
Review No. | Raised By | Issue Date | Issue | Status | Approved By | Closed date
LHWA_SDD_V1.0 | Fatma | 19/5/2022 | In login_2 feature inputs that are entered is username and password not eventObj | closed | Maha | 20/5/2022
| Fatma | 19/5/2022 | In login_3 there is an independent feature for the signUp in the code it only redict to the sign up page | closed | Maha | 20/5/2022
| Fatma | 19/5/2022 | In signUp feature in the page load function when the page is loaded it opens a connection this connection takes some inputs to establish it such as port number, IP address, username and password of the database | closed | Mai | 20/5/2022
| Fatma | 19/5/2022 | In admin-delete-content feature in the page load function when the page is loaded it opens a connection this connection takes some inputs to establish it such as port number, IP address, username and password of the database | closed | Mai | 20/5/2022
| Fatma | 19/5/2022 | in view article add the database inputs | closed | Mosatafa | 20/5/2022
| Fatma | 19/5/2022 | in upload video add the database inputs | closed | Mostafa | 20/5/2022
| Fatma | 19/5/2022 | inupload record add the database inputs | closed | Mostafa | 20/5/2022
| Fatma | 19/5/2022 | in admin delete user add the database inputs | closed | Maha | 20/5/2022

## PMP
ID | Raised By | Issue Date | Issue | Status | Approved By | Closed date
PMP_1_Quality_Managment_Plan | Fatma | 15/4/2022 | Pages Number need to be modified | Close | Fatma | 15/04/2022
PMP_2_Quality_Managment_Plan | Fatma | 15/4/2022 | In 1.1 section, following a good process need to be mentioned | Close | Fatma | 15/04/2022
PMP_3_Quality_Managment_Plan | Fatma | 15/4/2022 | In section 2.2 Environment and tools in impelementation needs to be added | Close | Fatma | 15/04/2022
PMP_4_Schedule/Time_Management | Fatma | 15/4/2022 | In section 2.2 figures 2.1 and 2.2 are reversed | Close | Fatma | 15/4/2022
PMP_5_Schedule/Time_Management | Fatma | 15/4/2022 | In section 2.2 the functionality of record void, rename it to uploadRec ordVoice | Close | Fatma | 15/4/2022
PMP_6_ConfigurationManagment | Fatma | 15/4/2022 | In section 4.1 Tailoring need to be more specific by clarfying its meaning to the customer in the glossary | Close | Fatma | 15/4/2022
PMP_7_ConfigurationManagment | Fatma | 15/4/2022 | In section 4.2 basline need to be more specific by clarfying its meaning to the customer in the glossary | Close | Fatma | 15/4/2022
PMP_8_Appendix A | Fatma | 15/4/2022 | missing this section in PMP document | Close | Fatma | 15/4/2022
PMP_9_Appendix A | Fatma | 15/4/2022 | Missing WBS Dicetionary location | Close | Fatma | 15/4/2022
PMP_10_Appendix A | Fatma | 15/4/2022 | Cannot open any of the links provided in location section | Close | Fatma | 15/4/2022
PMP_11_Risk_Management_plan | Radwa | 15/4/2022 | The Pages Number in the table of conent don't match the actual data the page numbers need to be updated | Close | Radwa | 15/4/2022
PMP_12_Risk_Management_plan | Radwa | 15/4/2022 | In 1.1 : Risk Management definition sentence need to be restructured | Close | Radwa | 15/4/2022
PMP_13_Risk_Management_plan | Radwa | 15/4/2022 | in 2.3.1 Probability : The Definitions of each probability need to be rephrase | Close | Radwa | 15/4/2022
PMP_14_Risk_Management_plan | Radwa | 15/4/2022 | in 2.4 in Mitigate : their is a spelling mistake "like adding more tests around the hi-risk areas" | Close | Radwa | 15/4/2022
PMP_15_Risk_Management_plan | Radwa | 15/4/2022 | in Appendix A : The Default message need to be changed | Close | Radwa | 15/4/2022
PMP_16_Risk_Management_log | Radwa | 15/4/2022 | Identify the Risk Areas Categories in the instructions | Close | Radwa | 15/4/2022
PMP_17_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log : Risk Management Log is duplicated | Close | Radwa | 15/4/2022
PMP_18_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log in RI_0 in Project Impact: The sentence need to be rephrase | Close | Radwa | 15/4/2022
PMP_19_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log in RI_3 in Risk Area : Budget need to be added | Close | Radwa | 15/4/2022
PMP_20_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log in RI_3 in Contingency Plan : non practical solution | Close | Radwa | 15/4/2022
PMP_21_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log the ID number 4 is missing and the the IDs starts with number 0 | Close | Radwa | 15/4/2022
PMP_22_Risk_Management_log | Radwa | 15/4/2022 | Grammer : In Risk_Tracking_Log in RI_5 in Project Impact : "some teams can't continue their job" | Close | Radwa | 15/4/2022
PMP_23_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log in RI_5 in Risk Area : Resources need to be added | Close | Radwa | 15/4/2022
PMP_24_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log in RI_6 swap Response Strategy with Contigency plan | Close | Radwa | 15/4/2022
PMP_25_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log Add a name column | Close | Radwa | 15/4/2022
PMP_26_Risk_Management_log | Radwa | 15/4/2022 | In Risk_Tracking_Log Change the ID naming convension | Close | Radwa | 15/4/2022
PMP_27_Issue_Management_Esclation Plan | Yara | 15/4/2022 | Project manager role should also be responsilbe for effectively manage and monitor issues on a regular basis, follow up with issue owners to ensure progress is being made towards resolution, and to report on the status of issues. | Close | Yara | 15/4/2022
PMP_28_Issue_Management_Esclation Plan | Yara | 15/4/2022 | step 4 2.2 "jeopardize" i think choose another simple word | Close | Yara | 15/4/2022
PMP_29_Project_Charter | Yara | 15/4/2022 | Project Name : Encyclopedia learning Hub | Close | Yara | 15/4/2022
PMP_30_Project_Charter | Yara | 15/4/2022 | 1. project Goals 1.1 Organ Objectives 1.1.7 schedule 5 weeks - 160 Hours (4 Hours every day) | Close | Yara | 15/4/2022
PMP_31_Project_Charter | Yara | 15/4/2022 | 1.project Goals 1.3 project specific objectives 1.3.1 web application not website | Close | Yara | 15/4/2022
PMP_32_Project_Charter | Yara | 15/4/2022 | 2.Deliverable . add PMP aslo | Close | Yara | 15/4/2022
PMP_33_Scope_Statement | Yara | 15/4/2022 | Scope Description In Scope Design --Web application not Website | Close | Yara | 15/4/2022
PMP_34_Scope_Statement | Yara | 15/4/2022 | Constraints Scope --Web application not Website | Close | Yara | 15/4/2022
PMP_35_WBS | Yara | 15/4/2022 | 3.1.6 Choose Categories not Seacrh for Categories | Close | Yara | 15/04/2022
PMP_36_WBS | Yara | 15/4/2022 | 3.2.5 Choose Categories not Seacrh for Categories | Close | Yara | 15/04/2022
PMP_37_WBS | Yara | 15/4/2022 | Missing "e" in word Encyclopedia web application | Close | Yara | 15/04/2022
PMP_38_WBS_Dictionary | Yara | 15/4/2022 | 1.2 Task Owner "yara&fatma" | Close | Yara | 15/4/2022
PMP_39_Introduction | Yara | 15/4/2022 | 1.2.1 web application not website | Close | Yara | 15/4/2022
PMP_40_Introduction | Yara | 15/4/2022 | 1.2.2 web application not website categories not fields | Close | Yara | 15/4/2022
PMP_41_Introduction | Yara | 15/4/2022 | 1.2.3 schedule 5 weeks - 160 Hours (4 Hours every day) | Close | Yara | 15/4/2022
PMP_42_Introduction | Yara | 15/4/2022 | 1.2.4 Maha: Designer | Close | Yara | 15/4/2022
PMP_43_Introduction | Yara | 15/4/2022 | 1.3.2 NO.4 only 3 admin features not 4 | Close | Yara | 15/4/2022
WBS_44_Project_Managment_Plan | Fatma | 30/4/2022 | Depends on 2.1.1(wrong dependency) and 2.1.8 (doesn't exist) | Close | Fatma | 2022-06-05
WBS_45_Quality_Managment_Plan | Fatma | 30/4/2022 | how it depends on number 3 | Close | Fatma | 2022-06-05
WBS_46_Configuration_Managment_Plan | Fatma | 30/4/2022 | how it depends on number 4 | Close | Fatma | 2022-06-05
WBS_47_Communication_Managment_Plan | Fatma | 30/4/2022 | 2.1.6 dependeoncy does not exist | Close | Fatma | 2022-06-05
WBS_48_Communication_Matrix | Fatma | 30/4/2022 | 2.1.6 dependency does not exist | Close | Fatma | 2022-06-05
WBS_49_Risk_Managment_Plan | Fatma | 30/4/2022 | 7 dependency doesnot exist | Close | Fatma | 2022-06-05
WBS_50_Risk_Log | Fatma | 30/4/2022 | risk log depends on wireframe design? | Close | Fatma | 2022-06-05
WBS_51_Frameworks&Tools | Fatma | 30/4/2022 | Dependency 1.3.3 doesnot exist | Close | Fatma | 2022-06-05
PMP_52_Revision_Date | Fatma | 30/4/2022 | missing revision date in version 1.2 | Close | Fatma | 2022-06-05
PMP_53_Folder_Structure_Concept | Fatma | 30/4/2022 | WBS is not in the concept folder | Close | Fatma | 2022-06-05
PMP_54_Folder_Structure_Definition_Design_HL | Fatma | 30/4/2022 | missing sequence diagram,erd,usecase and wireframes | Close | Fatma | 2022-06-05
PMP_55_Folder_Structure_Definition_Design_LL | Fatma | 30/4/2022 | missing sequence diagram | Close | Fatma | 2022-06-05
PMP_56_Folder_Structure_Definition_Requirements | Fatma | 30/4/2022 | missing validation specification | Close | Fatma | 2022-06-05
PMP_57_Folder_Structure_onitor&Control_Quality_Managment_Plan | Fatma | 30/4/2022 | missing audits and teceability matrix | Close | Fatma | 2022-06-05
PMP_58_Cover_Page | Mai | 2022-12-05 | The version and its date is not compatible | Close | Mai | 14/5/2022
PMP_59_Revision_History | Mai | 2022-12-05 | The date of last version is not compatible | Close | Mai | 14/5/2022
PMP_60_Constrains | Mai | 2022-12-05 | number of admin features is wrong | Close | Mai | 14/5/2022
PMP_61_Tools | Mai | 2022-12-05 | FrontEnd tools is needed to be changed | Close | Mai | 14/5/2022
PMP_62_WBS | Mai | 2022-12-05 | WBS Figure is not in the right place | Close | Mai | 14/5/2022
PMP_63_Folder_Structure | Mai | 2022-12-05 | Impact Analysis must be written in the table | Close | Mai | 14/5/2022
Project Charter_64_Project_Goals | Mai | 2022-12-05 | Goal number 7 in Organizational Goals needs to change | Close | Mai | 14/5/2022
Project Charter_65_Constrains | Mai | 2022-12-05 | Admins features need to be updated accprding to SRS | Close | Mai | 14/5/2022
Project Charter_66_Tools | Mai | 2022-12-05 | FrontEnd tools is needed to be changed | Close | Mai | 14/5/2022
Project Charter_66_Project_Organizational_Structure | Mai | 2022-12-05 | Not compatible roles with team structure in PMP | Close | Mai | 14/5/2022

## Design
ID | Raised By | Issue Date | Issue | Status | Approved By | Closed date
HLSD_01_Admin | Radwa | 30/4/2022 | File Name doesn't follow tha naming convension | Close | Radwa | 30/4/2022
HLSD_02_Admin | Radwa | 30/4/2022 | In SRS there is a condition if there is a poor connection in both the Functionalities | Close | Radwa | 30/4/2022
HLSD_03_RegisteredUser | Radwa | 30/4/2022 | There is no functionality called "clickOnSpecificCategory" | Close | Radwa | 30/4/2022
HLSD_04_RegisteredUser | Radwa | 30/4/2022 | Missing Functionality (Follow specific categories) | Close | Radwa | 30/4/2022
ERD_05 | Radwa | 30/4/2022 | The ID of each Entities aren't Unique | Close | Radwa | 30/4/2022
LLSD_06 | Mai | 30/4/2022 | The IDs of all diagrams don't match the SRS Features IDs | Close | Mai | 2022-04-05
LLSD_07_02AU | Mai | 30/4/2022 | in SRS, there is no mention that after logged in, the admin/user will be redirected to Home Page | Close | Mai | 2022-04-05
LLSD_08_03AU | Mai | 30/4/2022 | in SRS, there is no mention that after logged out, the admin/user will be redirected to Home Page | Close | Mai | 2022-04-05
LLSD_09_04AU | Mai | 30/4/2022 | Feature ID in SRS doesn't match ID in Diagram itself and Diagram's Name | Close | Mai | 2022-04-05
LLSD_10_04AU | Mai | 30/4/2022 | rectangle of Actor is missing "Admin" as an actor with User | Close | Mai | 2022-04-05
LLSD_11_04AU | Mai | 30/4/2022 | the button go in SRS but it doesn't found in the diagram | Close | Mai | 2022-04-05
LLSD_12_05U | Mai | 30/4/2022 | in SRS, there is no mention that after choosing category, the admin/user will be redirected to Category Page | Close | Mai | 2022-04-05
LLSD_13_05U | Mai | 30/4/2022 | in SRS, there is no mention that after publishing article, the admin/user will be redirected to be Redirected To Publish Article Page | Close | Mai | 2022-04-05
LLSD_14_06U | Mai | 30/4/2022 | in SRS, there is no mention that after choosing category, the admin/user will be redirected to Category Page | Close | Mai | 2022-04-05
LLSD_15_06U | Mai | 30/4/2022 | in SRS, there is no mention that after uploading video, the admin/userwill be redirected to be Redirected To Upload Video Page | Close | Mai | 2022-04-05
LLSD_16_08U | Mai | 30/4/2022 | In FR8_U the function name is different "upload Recorded Voice" | Close | Mai | 2022-04-05
Validation_17_UC_01 | Maha | 30/4/2022 | Web site not web application | Close | Maha | 2022-04-05
Validation_18_UC_01 | Maha | 30/4/2022 | Postconditions: created succssfully not "in" | Close | Maha | 2022-04-05
Validation_19_UC_02 | Maha | 30/4/2022 | "Login button will not be activated until the user fill all required fields" activated is not clear | Close | Maha | 2022-04-05
Validation_20_UC_03 | Maha | 30/4/2022 | postconditions: "The system shall display home page wit register & login button"mistake in "with" | Close | Maha | 2022-04-05
Validation_21_UC_04 | Maha | 30/4/2022 | "Main success scenario: Click on go button" there's no go button | Close | Maha | 2022-04-05
Validation_22_UC_04 | Maha | 30/4/2022 | Extentions: step 3 "User forget to choose " why the system gives alert if the user didn't choose? | Close | Maha | 2022-04-05
Validation_23_UC_09 | Maha | 2022-01-05 | Extentions: c- "either cutting the record in to several records or canceling the uploading process" | Close | Maha | 2022-06-05
Validation_24_UC_10 | Maha | 2022-01-05 | Choose language feature for admin and user | Close | Maha | 2022-04-05
Validation_25_UC_10 | Maha | 2022-01-05 | "User navigates through the website to show the Language section" in the navigation bar | Close | Maha | 2022-04-05
Validation_26_UC_10 | Maha | 2022-01-05 | Extentions: "alert" why alert if he didn't choose? it should be "if the desired language didn't appear" | Close | Maha | 2022-04-05
Validation_27_UC_12 | Maha | 2022-01-05 | "admin shall be able to delete any content" specifiy content | Close | Maha | 2022-04-05
Usecase_28 | Rana | 2022-01-05 | Missing user without register actor | Close | Rana | 2022-04-05
Usecase_29 | Rana | 2022-01-05 | Link new actor with "choose category & choose language & Register" use cases | Close | Rana | 2022-04-05
Usecase_30 | Rana | 2022-01-05 | Admin actor missing linking with "choose language" use case | Close | Rana | 2022-04-05
Wireframe_31_Admin | Rana | 2022-01-05 | Missing language button | Close | Rana | 2022-04-05
Wireframe_32_Registered user | Rana | 2022-01-05 | Missing language button | Close | Rana | 2022-04-05
Wireframe_33_Registered user | Rana | 2022-01-05 | In SRS in "Publish article,Upload video,Upload record" it doesn't mention that there Post dropdown list to choose from it it says button | Close | Rana | 2022-04-05
Wireframe_34_Registered user | Rana | 2022-01-05 | In SRS "Publish article" it is mention that the article will be uploaded not typed | Close | Rana | 2022-04-05
Wireframe_35_Registered user | Rana | 2022-01-05 | In SRS in "Publish article,Upload video,Upload record" it specify button name "Submit" and in wireframe it specify button name "Post" | Close | Rana | 2022-04-05
Wireframe_36_Registered user | Rana | 2022-01-05 | In wireframe "Upload video & Upload record" missinng buttons "browse","Upload", "Submit" | Close | Rana | 2022-04-05
Wireframe_37_Registered user | Rana | 2022-01-05 | In wireframe missing followed category page for notificatons | Close | Rana | 2022-04-05
Wireframe_38_Registered user | Rana | 2022-01-05 | In wireframe missing notification itself how it will be showed to user | Close | Rana | 2022-04-05
Wireframe_39_Registered user | Rana | 2022-01-05 | Is the bill icone for accessing nitification and followed category page or for following a specific category ?? if it is nfor following a specific category it only need to be showed in catego page but if it is for accessing followed categories then where is the following button in the category page | Close | Rana | 2022-04-05
Wireframe_40_Unregistered user | Rana | 2022-01-05 | missing choose language button | Close | Rana | 2022-04-05
FR11_AU_41_missed sequence Diagram | yara | 2022-03-05 | In the low level design there is sequence diagram missed for the system feature number 11 FR11_AU | Close | yara | 2022-04-05
FR1_UWR_42_missed sequence Diagram | yara | 2022-03-05 | In the low level design there is sequence diagram missed for the system feature number 1 | Close | yara | 2022-04-05

## SRS
Review No. | Raised By | Issue Date | Issue | Status | Approved By | Closed date
SRS_Version 1.0 | Mai | 15/4/2022 | Is each requirement atomic? | Close | Mai | 15/4/2022
| Mai | 15/4/2022 | Is each requirement Feasible? | Close | Mai | 15/4/2022
| Maha | 15/4/2022 | Is each requirement Understandable? | Close | Maha | 15/4/2022
| Rana | 14/04/2022 | Is each requirement has assigned priority? | Close | Rana | 15/04/2022
| Mai | 15/4/2022 | Is each requirement has a version? | Close | Mai | 15/4/2022
| Rana | 15/04/2022 | Are some software requirement traceable to its verification criteria? | Close | Rana | 15/04/2022
| Maha | 15/4/2022 | Is each software requirement traceable to a system requirement? | Close | Maha | 15/4/2022
| Rana | 15/04/2022 | Is each software requirement traceable to the system architecture? | Close | Rana | 15/04/2022
7491045203
SRS_Version 1.1 | Maha | 19/5/2022 | Functions ID | Close | Fatma | 19/5/2022
| Maha | 19/5/2022 | Dependencies Table | Close | Fatma | 19/5/2022
| Maha | 19/5/2022 | RTM should be edited | Close | Rana | 19/5/2022

## Options
Open
Close

## Progress_Chart
PMP | Open | 0 | SRS | Open | 0
| Closed | 67 |  | Closed | 11
| Total | 67 |  | Total | 11
Design | Open | 0
| Close | 42
| Total | 42