## WBS Dictionary
WORK BREAKDOWN STRUCTURE DICTIONARY
| PROJECT TITLE | PROJECT ID | COMPANY |  |  | VERSION
| Learning Hub Web Application | Team C | ITI |  |  | 1.2
TASK ID | TASK DESCRIPTION | DEPENDENT UPON | TASK OWNER | TASK STATUS | BEGIN DATE | DATE OF COMPLETION | ADDITIONAL INFO
1 | Planning |  |  | 100%
1.1 | Project Management Plan |  | Mai, Maha, Rana | 100% | 2022-10-04 | 15/4/2022
1.1.1 | Scope Management Plan | 1.1.1 | Mai | 100% | 2022-11-04 | 15/4/2022
| Project Charter | N/A | Maha , Mai | 100% | 2022-10-04 | 15/4/2022
1.1.2 | Change Management Plan | N/A | N/A | 0% | N/A | N/A | This plan will not be included in this phase.
1.1.3 | Schedule Time Management | 1.1.1 | Mai | 100% | 2022-12-04 | 22/4/2022
1.1.3.1 | MileStones | 1.1.1 | Radwa | 100% | 2022-11-04 | 15/4/2022
1.1.3.2 | Project Schedule | 1.1.1 | Radwa | 100% | 2022-11-04 | 15/4/2022
1.1.3.2 | Dependencies | 1.1.1 | Radwa | 100% | 2022-11-04 | 15/4/2022
1.1.4 | Quality Managemnt Plan |  | Rana | 100% | 2022-11-04 | 15/4/2022
1.1.5 | Configuration Management Plan |  | Rana | 100% | 2022-11-04 | 15/4/2022
1.1.6 | Commuincation Management Plan |  | Mai | 100% | 2022-10-04 | 15/4/2022
1.1.6.1 | Commuincation Matrix | 1.1.6 | Mai | 100% | 2022-10-04 | 15/4/2022
1.1.7 | Risk Management Plan |  | Maha | 100% | 2022-11-04 | 15/4/2022
1.1.7.1 | Risk Log | 1.1.7 | Mai | 100% | 2022-11-04 | 15/4/2022
1.2 | SRS | N/A | Yara, Fatma, Radwa | 100% | 2022-10-04 | 22/4/2022
1.2.1 | SIQ | 1.2 | All Team | 100% | 2022-09-04 | 2022-12-04
1.3 | Frameworks & Tools | 1.1.5 & 1.2.1 | Mai | 100% | 2022-12-04 | 15/4/2022
2 | Design |  |  | 100%
2.1 | Wireframe Design | 1.2 | Maha | 100% | 20/4/2022 | 27/4/2022
2.1.1 | Admin | 1.2 | Maha | 100% | 20/4/2022 | 27/4/2022
2.1.2 | Register User | 1.2 | Maha | 100% | 20/4/2022 | 27/4/2022
2.1.3 | Unregistered User | 1.2 | Maha | 100% | 20/4/2022 | 27/4/2022
2.2 | Architecture design | 1.2 | Radwa,Yara,Fatma | 100% | 22/4/2022 | 29/4/2022
2.2.1 | Usecases | 1.2 | Radwa | 100% | 22/4/2022 | 29/4/2022
2.2.2 | High Level Sequence diagrams | 1.2 | Fatma, Yara | 100% | 25/4/2022 | 29/4/2022
2.2.3 | Low Level Sequence Diagrams | 1.2 | Radwa | 100% | 24/4/2022 | 29/4/2022
2.3 | Database Design | 1.2 | Fatma, Yara | 100% | 23/4/2022 | 28/4/2022
2.3.1 | ERD | 1.2 | Fatma, Yara | 100% | 23/4/2022 | 28/4/2022
3 | Development |  |  | 4.167%
3.1 | Back-end | 2.1 | N/A | 0%
|  |  | N/A | 0%
3.2 | Front-End | 2.1.5 | N/A | 0%
|  |  | N/A | 0%
4 | Testing |  |  | 25%
4.1 | Unit Testing |  | N/A | 0%
4.2 | Integration testing |  | N/A | 0%
4.3 | System testing |  | N/A | 0%
4.4 | Acceptance testing |  | N/A | 100%