## Impact Analysis
Author | Mai Ashraf | [5 empty] | Mandatory field
Project Name | Learning Hub Web App | [5 empty] | Optional field
Version | 1 | [5 empty] | If mitigation not in place
Version Date | 13/5/2022
Title | Critical Activity Category, | Critical Activity Description | Area of Impact | Recovery Time Objective | Recovery Point Objective | Risk Mitigation | Minimum Service Level & Recovery Priority | Mitigation Owner | Review Date
Team Structure Change | Human Resource | There was a change happened in the team structure. A new member had been reallocated in the team instead of the team member who is responsible for the design and front-end development of the project. the new member lacked knowledge in this area so the team had to reassign the tasks again to make sure everyone is assigned the appropriate task he can finish within the time range. team members sat with him to make sure he is aware of the new role and responsibilities and that everything is clear. | Developement Roles and Responsibilities | 24 hours | Recovery to the point of loss | 1. Tasks had been reassigned to the members again on Trello. 2. The new member was assigned to tasks that match his knowledge. 3. Handover from the previous member to the member Tasks had been reassigned to the members again on Trello." |  |  | 14/5/2022
PM Absence | Team Management | PM of the team was available on the first day of the week of Milestone 3. Then there was an emergency that made him absent for four days. The PM contacted the team and assigned someone responsible for the team to make sure there was no delay in the delivery and keep tracking the implementation of the tasks. the situation wasn't good enough for the team due to the change that happened at the start of the week. new responsibility was reassigned to the team again to make sure everyone is aware of the situation | Roles and Responsibilities | 24 hours | Alternative Provided | 1. Team Member has been assigned to the responsibilities of PM (Maha)". 2. Tasks has been assigned to the members again on Trello. |  |  | 14/5/2022
Note on A6: Forbes, David: Title should capture the essence of the activity and briefly describe it
Note on B6: Forbes, David: It may be helpful to identify a broad category for the activity but this is optional. Example categories are identified below row 11
Note on C6: Forbes, David: Describe the activity here. Include sufficient information to identify the area, scope, causes, consequences and other factors that will describe the activity in a way which is understandable to someone who is not from your area or discipline
Note on D6: Forbes, David: It may be helpful to identfy the area of impcat; one or more areas may be applicable
Note on E6: Forbes, David: This is the maximum tolerable period of disruption. Identify how long before the impact of the disruption becomes intolerable. e.g. within 24hrs; 1 week; 2 weeks; a month; a year. This will then inform the mitigation required to recover the activity within that time frame. As a general rule the more quickly recovery is required the greater the expense of the mitigation. Thus there should be consideration of what mitigation is appropriate.
Note on F6: Forbes, David: Identify the point to which the activity should be recovered. e.g. Does the activity need to be recovered to the condition it was at when it was disrupted? This will also inform the mitigation required and like the RTO has cost implications. Recovery to the point of loss may be more costly than recovery to "within the last 24 hours". What is appropriate for this activity?
Note on G6: Forbes, David: This is the pivotal column and focus of the AIA exercise. What mitigation is required to achieve the desired Recovery Point, Recovery Time and Minimum Service Level/Recovery Priority? Please also note whether this is in place or, if not, what action is required and by whom to put it in place.
Note on H6: Forbes, David: If an area has multiple activities, identify the order in which they should be restored. To assist the recovery teams it may also be helpful to identify the minimum acceptable service level. E.g. it may be acceptable for some infrequently used areas to be restored last but it may also be necessary for a number of activities to be restored simultaneously before an acceptable level of service/activity can be achieved. This information will also assist in identifying the appropriate provision of mitigation.
Note on I6: Forbes, David: Person with the accountability and authority to be best placed to manage the mitigation. Responsible for securing agreement to: • Identification and implementation of the appropriate mitigation required to improve resilience and facilitate recovery • Key milestones and review dates
Note on J6: Forbes, David: The date for delivery of the next key milestone